## Sheet1
Goal | Phase | Milestone | Task | Task Holder | Man-hours | Status
Deploy Barq-lite to Production | Planning | Gather Req | Gather the Customer Req | omar | 0.5 | ✅ Completed
|  |  | Write BRD (Business Requirements Document) | omar | 0.5 | ✅ Completed
|  | Approval | Present and get client sign-off | omar | 0.5 | ✅ Completed
|  | Init Resources | Create logs directory, configure ownership and permissions | Omar | 0.5 | ✅ Completed
|  |  | Create jars directory and deploy initial artifacts | Omar |  | ✅ Completed
|  |  | Establish TLS directory structure | Omar |  | ✅ Completed
|  |  | Generate initial documentation skeleton | Omar | 0.5 | ✅ Completed
| Logging | Logging Framework | Develop log rotation script (logrotate) | Omar | 0.75 | ✅ Completed
|  |  | Create tests for log rotation outcomes | Omar | 0.5 | ✅ Completed
|  |  | Schedule cron job for log rotation | Omar | 0.25 | ✅ Completed
| Certificates | Cert Management Script | Implement certificate issuance & renewal script | Omar | 0.75 | ✅ Completed
|  | Cert Management Testing | Write integration tests for certificate script | Omar | 0.5 | ✅ Completed
|  | Cert Management Cron | Configure cron job for certificate renewal | Omar | 0.25 | ✅ Completed
| Automation | Ansible install & Playbooks | Develop playbook for JAR deployment | Omar | 0.5 | ✅ Completed
|  | Automation Testing | Build quick smoke tests for Ansible runs | Omar | 0.75 | ✅ Completed
|  | Documentation | Document Ansible variables & usage guide | Omar | 0.5 | ✅ Completed
| Testing | Service Validation | Validate service endpoints | Omar | 0.5 | ✅ Completed
|  | End-to-End Test | Execute full suite: env → logs → certs → service | Omar | 0.5 | ✅ Completed
| Containerization | Docker install & Build image | Author Dockerfile, build image locally | Omar | 1 | ✅ Completed
|  | Image Push | Push final Docker image to registry | Omar | 0.25 | ✅ Completed
| LoadBalancing | ensure avaialbility | install & Configure Nginx LB container & health checks | Omar | 0.5 | ✅ Completed
| Deployment | Deploy to Staging | Deploy in staging server for client review | omar | 0.5 | ✅ Completed
|  | Deploy to Production | Final release deployment | omar | 0.5 | ✅ Completed
| Post-Deployment | Maintenance Plan | Define support/maintenance procedures | omar | 0.5 | ✅ Completed
|  | Feedback & Iteration | Collect user feedback, plan improvements | omar | 0.5 | ✅ Completed | Total: 10 hours
Document the Full process